## Task Distribution
TokenFest — Week 1 Task Distribution
Week 1 goal: working end-to-end code (no automated tests yet). The Week 1 code was originally written by Phoebe L and is split by module; each member adds their package from their own GitHub account and owns that module from now on. Merge order: Member 1 → Member 2 → Member 3.
Member | Module | Directories / files | Week 1 work | Depends on | Acceptance criteria | Branch
Member 1: Phoebe L | Gateway core: proxy, routing, providers | backend/.../gateway/proxy/ backend/.../gateway/provider/ backend/.../gateway/crypto/ backend/.../gateway/config/ backend/.../gateway/web/ GatewayApplication.java backend/pom.xml, mvnw, .mvn/ resources/application*.yml README.md, CONTRIBUTING.md, GIT_WORKFLOW.md, .gitignore docs/architecture.md, docs/SRS.docx | 1. Create the private team repo and push package 1 to main 2. Run the backend (H2) and send real requests: OpenAI format (normal + streaming) and Anthropic format 3. Turn off the first provider and check fallback to the second 4. Document the request flow and settings in docs/architecture.md 5. Fix problems found | Member 2: KeyInfo, LimitChecker, UsageRecorder (agree before changing their signatures) | • ./mvnw package succeeds on a clean clone • Normal + streaming requests in both formats work and appear in the request log • Fallback works • architecture.md updated • PR reviewed by another member | main (package 1) feature/week1-member1
Member 2: Xiaohan Wang | Keys, auth and accounting | backend/.../gateway/keys/ backend/.../gateway/auth/ backend/.../gateway/limits/ backend/.../gateway/usage/ backend/.../gateway/alerts/ backend/.../gateway/stats/ backend/.../gateway/export/ backend/.../gateway/settings/ backend/.../gateway/user/ backend/.../gateway/maintenance/ backend/.../gateway/domain/ backend/.../gateway/repository/ resources/db/migration/ docs/api.md, docs/database.md | 1. Read the module, api.md and database.md; note anything unclear 2. With curl, go through: admin login; create / update / disable / regenerate / delete key; key login; budget 429; rate-limit 429; alert settings + webhook; stats; CSV export; member API 3. Add a "Walkthrough with curl" section to docs/api.md 4. Fix problems found or open issues | Member 1: proxy produces usage records Member 3 uses this API (tell them before changing response fields) | • Every admin and user endpoint called and works as documented • Budget and rate-limit 429 checked by hand • curl walkthrough in api.md • Schema changes only as new V2__ migrations • PR reviewed by another member | feature/week1-member2
Member 3: Mingzhu Wan | Dashboard and deployment | frontend/ (all) docker-compose.yml backend/Dockerfile, backend/.dockerignore .env.example docs/user-guide.md docs/deployment.md docs/wireframes.md | 1. Run the full stack with docker compose up -d --build 2. Check every page (Overview, Requests, Providers, Keys, Settings, member dashboard) against wireframes.md 3. Fix the lint warning at frontend/src/components/ui.tsx:75 4. Add screenshots to user-guide.md; check deployment.md 5. Fix UI problems found | Member 2: API (api.ts / types.ts must match api.md) Member 1: backend build for the Docker image | • docker compose starts all three services on a clean clone; dashboard opens on :8080 • Every page loads and shows a test request • npm run build and npm run lint pass with no warnings • User guide has screenshots • PR reviewed by another member | feature/week1-member3

## Functionality Checklist
Week 1 Functionality Checklist
Everything below is in the Week 1 code. Tests, load tests and CI come in a later week.
# | Function | Owner | Included
1 | OpenAI-compatible /v1/chat/completions, /v1/models, /v1/responses, /v1/embeddings | Member 1 | Yes
2 | Anthropic-compatible /v1/messages (+ count_tokens) | Member 1 | Yes
3 | Streaming (SSE) passthrough with usage tracking | Member 1 | Yes
4 | Routing by model and priority; fallback on 408/429/5xx/timeout; provider cool-down | Member 1 | Yes
5 | Provider management; provider keys encrypted (AES-GCM) | Member 1 | Yes
6 | Team member keys (tf-..., SHA-256 hash, shown once, regenerate) | Member 2 | Yes
7 | Admin login (JWT), member key login, login throttling | Member 2 | Yes
8 | Monthly budget and rate limit per key | Member 2 | Yes
9 | Token and cost tracking; request log; daily totals | Member 2 | Yes
10 | Budget alerts (webhook, email) and settings | Member 2 | Yes
11 | Stats API, CSV export, member API, nightly log cleanup | Member 2 | Yes
12 | Database schema (Flyway), PostgreSQL + H2 | Member 2 | Yes
13 | Admin dashboard: Overview, Requests, Providers, Keys, Settings | Member 3 | Yes
14 | Member dashboard | Member 3 | Yes
15 | Docker Compose deployment (PostgreSQL + backend + nginx) | Member 3 | Yes
— | Automated tests (backend, frontend, SDK end-to-end), load test, CI | Later week | No